## Sheet1
Work Breakdown | [8 empty] | Status values: | Priority values
Category | Work Item | Status | Priority | Cost (hrs) | Start Date | End Date | Owner | Reviewer | Active | 1
Documentation | Project timeline and work breakdown. | Active | 1 | 0.5 | 2023-05-14 | 2023-01-16 | Maddox | Maddox | Cut | 2
Documentation | Project charter and statement | Active | 1 | 1 | 2023-05-15 | 2023-05-18 | Maddox | Maddox | Done, not tested | 3
Documentation | create UML diagrams for "Player", "AI", "GameState" | Active | 2 | 0.5 | 2023-05-19 | 2023-05-21 | Maddox | Maddox | Done, tested
Product | Code Main class loop and player/ai interactions | Active | 3 | 1 | 2023-05-25 | 2023-05-27 | Maddox | Maddox
Product | Code Player class methods and variables | Active | 3 | 1 | 2023-05-27 | 2023-05-29 | Maddox | Maddox
Product | Code GameState data structure, variables, and methods | Active | 3 | 2 | 2023-05-29 | 2023-06-01 | Maddox | Maddox
Product | Code AI minimax search algoritm for adversarial decision making | Active | 1 | 1 | 2023-06-01 | 2023-06-02 | Maddox | Maddox
Product | Implement alpha-beta pruning to speed up runtime computation | Active | 3 | 1 | 2023-06-02 | 2023-06-03 | Maddox | Maddox
Product | Implement a cutoff integer to halt indefinite searching | Active | 3 | 1 | 2023-06-03 | 2023-06-05 | Maddox | Maddox
Product Management | Submit Project | Active | 3 | 0.25 | 2023-06-05 | 2023-06-05 | Maddox | Maddox